Smart Parking Platform Project - $oftware ¢orp.

Homework 2

Gerardo Vera

CIS 4374

September 17, 2026

1. Workdown Breakdown Structure

1. Authentication

- 1.1 Registration

  - 1.1.1 Account creation

  - 1.1.2 Account verification through email

- 1.2 Login

  - 1.2.1 Email and password input credentials

  - 1.2.2 Password reset

- 1.3 Sessions

  - 1.3.1 Logout feature

  - 1.3.2 Session time out

2. User/Operator Setup

- 2.1 User Profile

  - 2.1.1 Contact information

  - 2.1.2 Vehicle information

  - 2.1.3 Delete account feature

- 2.2 Operator Profile

  - Operator information

  - Ability to assign garages

- 2.3 Access Permissions

3. Dashboard

- 3.1 Garage Management

  - 3.1.1 Edit and add garages

  - 3.1.2 Update parking spaces and prices

- 3.2 Parking Search

  - 3.2.1 Real-time availability on maps

  - 3.2.2 Direction to garages

- 3.3 Reservation

  - 3.3.1 Garage selection and booking

  - 3.3.2 Reservation cancellation

- 3.4 Notification

  - 3.4.1 Booking confirmation and number

4. Payments

- 4.1 Payment Process

  - 4.1.1 Payment option

  - 4.1.2 Determine if payment went through

- 4.2 Payment Confirmation

  - 4.2.1 Digital Receipt

  - 4.2.2 Download Receipt Feature

5. Reporting

- 5.1 Availability Report

  - 5.1.1 Current garage availability

  - 5.1.2 Trends in garages availability

- 5.2 Financial Report

  - 5.2.1 Revenue in each garage

- 5.3 Reservation History

  - 5.3.1 Upcoming reservation

  - 5.3.2 Completed and canceled reservation

2. Project Timeline

2.1 Timeline

|  | Tasks | Start | Finish | Duration (days) |
| --- | --- | --- | --- | --- |
| 1 | Requirements and scope | 10/5/26 | 10/9/26 | 5 |
| 2 | System prototypes | 10/12/26 | 10/23/26 | 12 |
| 3 | Authentication and setups | 10/26/26 | 11/6/26 | 12 |
| 4 | Garage management and monitoring | 10/26/26 | 11/13/26 | 19 |
| 5 | Parking search and maps | 11/02/26 | 11/20/26 | 19 |
| 6 | Reservation and history | 11/09/26 | 11/27/26 | 19 |
| 7 | Payments and confirmation | 11/16/26 | 11/27/26 | 12 |
| 8 | Navigation maps and notifications | 11/16/26 | 11/27/26 | 12 |
| 9 | Reporting integration | 11/23/26 | 12/04/26 | 12 |
| 10 | System testing and integration | 12/07/26 | 12/11/26 | 5 |
| 11 | Finalize testing and fixes | 12/14/26 | 12/17/26 | 4 |
| 12 | Deployment and complete design | 12/18/26 | 12/18/26 | 1 |

2.2 Gantt Chart